## Backlog Report
Gestão de Recursos Humanos
Tema | ID | História de Usuário | Critérios de Aceitação | Comentários | Sprint | Status | 50 | 90
Integration with HR ERP Systems | 1.1 | As an HR manager, I want the system to integrate seamlessly with our existing HR ERP so that data flows without manual intervention. | "a) System automatically syncs data with the ERP daily. b) Users can view ERP data within the system without errors. c) Integration logs are maintained for troubleshooting." | Ensures continuous data flow and accessibility for HR management." |  |  | 8 | 15
| 1.2 | As an IT administrator, I want the system to handle ERP data changes efficiently so that updates are reflected in real-time. | a) Data changes in the ERP are reflected in the system within 5 minutes. b) Notifications are sent to users upon data update. c) System maintains version control of data updates. | "Supports IT in managing and monitoring ERP data integrations." |  |  | 5 | 10
| 1.3 | As an HR executive, I want to ensure that the data integrity is maintained during the integration process so that HR decisions are based on accurate information. | a) System performs data validation checks during sync. b) Any data discrepancies are flagged and reported. c) Manual override options are available for critical data corrections. | "Critical for maintaining the reliability and accuracy of HR data." |  |  | 6 | 12
| 1.4 | As an employee, I want my personal and performance data from the HR ERP to be available in the new system so that I can have a single point of access. | a) Employee data is migrated and available in the new system. b) Personal and performance data is updated in real-time. c) Employees can view and edit their information within system permissions. | "Facilitates employee access to their own data, enhancing user experience." |  |  | 4 | 8
| 1.5 | As a compliance officer, I want the integration to comply with data protection regulations so that the organization remains compliant with legal requirements. | a) Data transfer processes adhere to GDPR and other relevant regulations. b) System encrypts data during transfer. c) Audit logs are maintained for all data sync activities. | "Ensures the system meets legal standards for data security and privacy." |  |  | 7 | 14
| Total do tema 'Integration with HR ERP Systems' |  |  | 0.0 pontos
Automated Performance Evaluation Workflows | 2.1 | "As an HR manager, I want the system to automatically initiate performance evaluations based on predefined schedules so that evaluations are conducted timely." | "a) System triggers evaluations based on predefined schedules. b) Notifications are sent to managers and employees when evaluations are initiated. c) Evaluation forms are pre-populated with relevant data." | "Ensures timely and systematic evaluation processes." |  |  | 8 | 15
| 2.2 | "As a team lead, I want to be notified when a performance evaluation is due for my team members so that I can provide timely feedback." | "a) System sends notifications to team leads two weeks before evaluations are due. b) Team leads can access and review evaluation forms. c) System tracks notification acknowledgments." | "Facilitates proactive feedback and preparation by team leads." |  |  | 5 | 10
| 2.3 | "As an employee, I want to receive reminders to complete my self-evaluation so that I can reflect on my performance before the review meeting." | "As an employee, I want to receive reminders to complete my self-evaluation so that I can reflect on my performance before the review meeting." | "Supports employees in engaging actively in their performance review process." |  |  | 4 | 8
| 2.4 | "As an HR executive, I want to track the progress of ongoing performance evaluations so that I can ensure all evaluations are completed on time." | "a) System provides a dashboard showing the status of all ongoing evaluations. b) HR executives can view which evaluations are pending, in progress, or completed. c) System generates reports on evaluation completion rates." | "Enables HR executives to monitor and ensure timely completion of evaluations." |  |  | 6 | 12
| 2.5 | "As an HR manager, I want the system to automatically escalate overdue performance evaluations to higher management so that delays are addressed promptly." | "a) Overdue evaluations are flagged and escalated to higher management. b) Notifications are sent to higher management for overdue evaluations. c) System logs all escalations for audit purposes." | "Helps in managing and mitigating delays in the evaluation process efficiently." |  |  | 7 | 14
| 2.6 | "As an IT administrator, I want to ensure that the automated workflows run smoothly without errors so that the evaluation process is not disrupted." | "a) System logs all automated workflow activities. b) Errors in the workflow are automatically reported to IT. c) IT administrators have tools to monitor and troubleshoot workflows." | "Critical for maintaining system integrity and smooth operation of automated evaluation workflows." |  |  | 8 | 10
| Total do tema 'Automated Performance Evaluation Workflows' |  |  | 0.0 pontos
Data Collection and Analysis | 3.1 | "As an HR analyst, I want the system to collect performance data from various sources so that I can analyze overall employee performance." | "a) System integrates with multiple data sources (e.g., sales data, project management tools). b) Performance data is collected and stored in a centralized database. c) Data is updated in real-time or at scheduled intervals." | "Ensures comprehensive data collection for performance analysis." |  |  | 10 | 20
| 3.2 | "As an HR manager, I want to generate performance reports based on collected data so that I can make informed decisions." | "a) System provides a user-friendly interface for generating reports. b) Reports can be customized based on various parameters (e.g., date range, department). c) Generated reports are accurate and exportable in multiple formats (e.g., PDF, Excel)." | "Facilitates decision-making through detailed performance reports." |  |  | 8 | 16
| 3.3 | "As an employee, I want to access my performance data so that I can track my progress over time." | "a) Employees can securely access their own performance data. b) Data is presented in an easy-to-understand format. c) Employees can download their performance reports." | "Empowers employees to monitor their own performance." |  |  | 5 | 10
| 3.4 | "As a data analyst, I want to use advanced analytical tools to identify performance trends so that I can provide insights to HR and management." | "a) System supports advanced analytics (e.g., trend analysis, predictive analytics). b) Data visualization tools (e.g., charts, graphs) are available for better insights. c) Analysts can apply various filters and parameters to refine the analysis." | "Enables in-depth analysis of performance data for strategic insights." |  |  | 10 | 20
| 3.5 | "As an HR executive, I want to ensure that the collected data is accurate and free from errors so that decisions are based on reliable information." | "a) System performs regular data validation checks. b) Inconsistencies or errors in data are flagged and corrected. c) Audit logs are maintained for all data collection and validation activities." | "Maintains data integrity for accurate decision-making." |  |  | 7 | 14
| 3.6 | "As a department head, I want to compare the performance data of different teams so that I can identify areas for improvement." | "a) System allows comparison of performance data across teams. b) Comparative reports highlight key performance indicators (KPIs) and metrics. c) Department heads can generate and export comparison reports." | "Provides comparative insights for team performance improvement." |  |  | 6 | 12
| 3.7 | "As an IT administrator, I want to ensure the performance data is securely stored and backed up so that it is protected against data loss." | "a) Data is stored in a secure and encrypted database. b) Regular backups are performed and stored securely. c) Access to performance data is controlled through robust access management protocols." | "Ensures the security and availability of performance data." |  |  | 5 | 10
Total do tema 'Data Collection and Analysis'
Multisource Feedback Collection | 4.1 | "As an HR manager, I want to collect feedback from multiple sources (peers, managers, subordinates) so that I can get a comprehensive view of employee performance." | "a) System supports feedback submission from various roles (peers, managers, subordinates). b) Feedback forms are customizable for different roles. c) Feedback is stored securely and accessible for analysis." | "Enables a holistic assessment of employee performance by gathering diverse perspectives." |  |  | 10 | 20
| 4.2 | "As an employee, I want to provide anonymous feedback about my colleagues so that I can contribute to a fair evaluation process." | "a) System allows anonymous feedback submission. b) Anonymity of feedback providers is maintained. c) Feedback is collected and used in performance evaluations without revealing the identity of the provider." | "Promotes honest and unbiased feedback by maintaining confidentiality." |  |  | 8 | 16
| 4.3 | "As a manager, I want to review and approve the feedback submitted by my team members so that I can ensure its relevance and appropriateness." | "a) Managers can access and review submitted feedback. b) Managers can approve, reject, or request modifications to the feedback. c) Approved feedback is included in the performance evaluation process." | "Facilitates managerial oversight to maintain quality and relevance of feedback." |  |  | 7 | 14
| 4.4 | "As an HR analyst, I want to aggregate feedback from different sources so that I can identify common themes and areas for improvement." | "a) System aggregates feedback from various sources. b) Aggregated feedback is presented in a comprehensive report. c) Reports highlight common themes, strengths, and areas for improvement." | "Supports comprehensive analysis to derive actionable insights from feedback data." |  |  | 10 | 20
| 4.5 | "As an employee, I want to view the feedback I have received from my colleagues so that I can understand how I am perceived by others." | "a) Employees can securely access the feedback received. b) Feedback is presented in a constructive and anonymous manner. c) Employees can download their feedback reports." | "Empowers employees by providing access to personal feedback for self-improvement." |  |  | 6 | 12
| 4.6 | "As an HR executive, I want to ensure that the feedback collection process is fair and unbiased so that the evaluations are reliable." | "a) System includes checks to prevent biased or inappropriate feedback. b) Feedback collection process is transparent and consistent. c) Regular audits are conducted to ensure fairness and integrity." | "Guarantees the integrity and fairness of the feedback process, crucial for valid evaluations." |  |  | 8 | 16
| 4.7 | "As a feedback provider, I want to receive prompts and reminders to submit feedback so that I can complete my evaluations on time." | "a) System sends automated prompts and reminders to feedback providers. b) Reminders are customizable in terms of frequency and timing. c) Feedback providers receive notifications until their feedback is submitted." | "Ensures timely submission of feedback by providing necessary prompts and reminders." |  |  | 8 | 10
| 4.8 | "As an HR administrator, I want to configure and customize the feedback forms so that they are relevant to different roles and departments." | "a) Feedback forms are customizable for different roles and departments. b) Administrators can create, modify, and delete feedback forms. c) Changes to feedback forms are reflected in the system immediately." | "Allows for tailored feedback mechanisms to suit the specific needs of various organizational roles and departments." |  |  | 7 | 14
| Total do tema 'Multisource Feedback Collection' |  |  | 0.0 pontos
Customizable Evaluation Forms and Workflows | 5.1 | "As an HR manager, I want to create customized evaluation forms tailored to specific job roles so that the evaluations are relevant and accurate." | "a) System allows creation of custom evaluation forms. b) Forms can be tailored to specific job roles. c) Custom forms are saved and accessible for future use." | "Ensures evaluations are role-specific and meaningful." |  |  | 8 | 16
| 5.2 | "As an HR administrator, I want to modify existing evaluation forms to reflect changes in job responsibilities so that evaluations remain current." | "a) Existing forms can be edited and updated. b) Modifications are tracked and versioned. c) Updated forms are instantly available for use." | "Keeps evaluation forms up-to-date with job changes." |  |  | 7 | 14
| 5.3 | "As an employee, I want to access and complete my evaluation forms online so that the process is convenient and efficient." | "a) Employees can access evaluation forms through a secure portal. b) Forms are user-friendly and easy to complete. c) Completed forms are submitted electronically and confirmation is provided." | "Facilitates easy and efficient evaluation process for employees." |  |  | 6 | 12
| 5.4 | "As a manager, I want to review and provide feedback on my team's evaluations so that I can contribute to their development." | "a) Managers can access and review team evaluation forms. b) Managers can add comments and feedback. c) Feedback is saved and included in the final evaluation report." | "Enables managers to actively participate in the development of their team." |  |  | 7 | 14
| 5.5 | "As an HR executive, I want to define and automate evaluation workflows so that the evaluation process is consistent and timely." | "a) System supports the creation of automated evaluation workflows. b) Workflows can be customized to include specific steps and approvals. c) Automated reminders and notifications are sent to ensure timely completion." | "Streamlines the evaluation process through automation." |  |  | 8 | 16
| 5.6 | "As an HR analyst, I want to generate reports based on the evaluation forms to analyze employee performance trends." | "a) System generates reports from completed evaluation forms. b) Reports highlight performance trends and areas for improvement. c) Reports can be filtered and customized as needed." | "Provides insights into employee performance to guide HR decisions." |  |  | 9 | 18
| 5.7 | "As an employee, I want to receive feedback from my evaluation so that I can understand my strengths and areas for improvement." | "a) Employees receive notifications when evaluations are complete. b) Feedback is accessible through the employee portal. c) Feedback is presented constructively and includes actionable insights." | "Empowers employees with feedback for personal development." |  |  | 5 | 10
| 5.8 | "As an HR manager, I want to set up evaluation cycles and deadlines so that the evaluation process is organized and timely." | "a) System allows the setup of evaluation cycles and deadlines. b) Evaluation cycles are visible to all relevant users. c) Reminders and alerts are sent to ensure deadlines are met." | "Ensures the evaluation process is systematic and adheres to schedules." |  |  | 6 | 12
| 5.9 | "As a feedback provider, I want to save my progress when completing evaluation forms so that I can finish them at my convenience." | "a) Feedback providers can save their progress on forms. b) Saved forms can be resumed and completed later. c) Partial submissions are secure and not lost." | "Allows feedback providers the flexibility to complete evaluations at their own pace." |  |  | 4 | 5
| Total do tema 'Customizable Evaluation Forms and Workflows' |  |  | 0.0 pontos
Digital Documentation and Archiving | 6.1 | "As an HR manager, I want to store all evaluation records digitally so that I can easily access and manage employee performance data." | "a) System allows digital storage of evaluation records. b) Records are easily retrievable through search functionality. c) Storage meets data security and compliance standards." | "Facilitates easy access and management of performance data." |  |  | 8 | 16
| 6.2 | "As an HR administrator, I want to archive old evaluation records to maintain a clean and current working database while retaining historical data." | "a) System supports archiving of old records. b) Archived records are retrievable for historical reference. c) Archiving process does not affect current data operations." | "Maintains database cleanliness and allows historical reference." |  |  | 7 | 14
| 6.3 | "As an employee, I want to access my past evaluation records so that I can review my performance history." | "a) Employees can access their own evaluation history through a secure portal. b) Records are presented in a user-friendly format. c) Access to records is compliant with data privacy regulations." | "Enables employees to review their performance history." |  |  | 6 | 12
| 6.4 | "As an HR executive, I want to ensure that all digital records are securely backed up to prevent data loss." | "a) System includes automated backup of all digital records. b) Backup processes run at regular intervals. c) Backups are stored securely and can be restored as needed." | "Prevents data loss through secure and regular backups." |  |  | 8 | 16
| 6.5 | "As an HR analyst, I want to generate reports from archived records to analyze long-term performance trends." | "a) System can generate reports using both current and archived data. b) Reports highlight long-term performance trends. c) Reports can be customized and filtered." | "Provides insights into long-term performance trends." |  |  | 9 | 18
| 6.6 | "As an IT administrator, I want to set access permissions for digital records to ensure that only authorized personnel can view or modify them." | "a) System supports role-based access controls. b) Access permissions can be easily managed and updated. c) Audit logs track access and modifications to records." | "Ensures security and proper access to digital records." |  |  | 7 | 14
| 6.7 | "As an HR manager, I want to receive notifications for any changes or updates made to the digital records so that I can maintain oversight." | "a) System sends notifications for any changes to records. b) Notifications include details of the changes made. c) HR managers can view a log of all changes." | "Maintains oversight on changes to digital records." |  |  | 6 | 12
| 6.8 | "As a compliance officer, I want to ensure that all digital records are stored in compliance with legal and regulatory requirements." | "a) System complies with relevant data protection and privacy laws. b) Compliance features are regularly updated to reflect changes in regulations. c) Compliance reports can be generated to demonstrate adherence." | "Ensures compliance with legal and regulatory requirements." |  |  | 8 | 16
| 6.9 | "As an HR executive, I want to ensure that all evaluation records are stored with version control to track changes over time." | "a) System supports version control for all records. b) Historical versions of records can be accessed and reviewed. c) Changes between versions are clearly documented." | "Tracks changes to records over time with version control." |  |  | 7 | 14
| 6.10 | "As an HR manager, I want to integrate the digital documentation system with other HR systems to streamline data flow and reduce manual data entry." | "a) System supports integration with other HR systems. b) Data flows seamlessly between systems. c) Integration reduces the need for manual data entry and errors." | "Streamlines data flow and reduces manual data entry." |  |  | 9 | 18
| Total do tema 'Digital Documentation and Archiving' |  |  | 0.0 pontos
Legal and Executive Reviews | 7.1 | "As an HR manager, I want to attach legal reviews to performance evaluations to ensure compliance with employment laws." | "a) System allows attachment of legal reviews to evaluations. b) Legal reviews are securely stored and linked to the corresponding evaluation. c) Only authorized personnel can access legal reviews." | "Ensures compliance with employment laws." |  |  | 6 | 12
| 7.2 | "As an executive, I want to review and approve performance evaluations before finalization to ensure they align with company policies." | "a) Executives can access and review evaluations before they are finalized. b) System provides a workflow for review and approval. c) Notifications are sent to executives when evaluations are ready for review." | "Aligns evaluations with company policies before finalization." |  |  | 7 | 14
| 7.3 | "As a legal advisor, I want to provide feedback on performance evaluations to ensure they meet all legal requirements." | "a) Legal advisors can access and comment on evaluations. b) Feedback from legal advisors is tracked and documented. c) Evaluations cannot be finalized until legal feedback is addressed." | "Ensures evaluations meet all legal requirements." |  |  | 8 | 16
| 7.4 | "As an HR executive, I want to ensure that all evaluations involving disciplinary actions have a legal review to mitigate risks." | "a) System flags evaluations involving disciplinary actions for mandatory legal review. b) Legal reviews are attached and completed before evaluations are finalized. c) Notifications are sent to legal advisors for required reviews." | "Mitigates risks associated with disciplinary actions." |  |  | 7 | 14
| 7.5 | "As an HR manager, I want to integrate legal review processes into the performance evaluation workflow to streamline operations." | "a) Legal review steps are integrated into the performance evaluation workflow. b) System ensures all required legal reviews are completed. c) Integration reduces the need for separate legal review processes." | "Streamlines operations by integrating legal reviews into the workflow." |  |  | 8 | 16
| 7.6 | "As an HR executive, I want to generate reports on the status of legal reviews for performance evaluations to monitor compliance." | "a) System can generate reports on the status of legal reviews. b) Reports highlight evaluations pending legal review. c) Reports can be customized and filtered by various criteria." | "Monitors compliance through status reports on legal reviews." |  |  | 9 | 18
| 7.7 | "As an HR manager, I want to receive notifications when a legal review is completed to proceed with the evaluation process." | "a) System sends notifications when legal reviews are completed. b) Notifications include details of the review status. c) HR managers can proceed with the evaluation process upon receiving notifications." | "Keeps HR managers informed to proceed with evaluations." |  |  | 7 | 14
| 7.8 | "As a compliance officer, I want to ensure that all legal reviews are stored in compliance with legal and regulatory requirements." | "a) System stores legal reviews in compliance with data protection laws. b) Compliance features are regularly updated to reflect changes in regulations. c) Compliance reports can be generated to demonstrate adherence." | "Ensures storage compliance with legal and regulatory requirements." |  |  | 8 | 16
| 7.9 | "As an HR executive, I want to review the history of legal feedback and decisions on performance evaluations to ensure consistent decision-making." | "a) System maintains a history of legal feedback and decisions. b) Historical records can be accessed and reviewed. c) Changes and decisions are clearly documented for consistency." | "Ensures consistent decision-making through historical review of legal feedback." |  |  | 6 | 12
| 7.10 | "As an HR manager, I want to integrate the legal review system with other HR systems to ensure seamless data flow and reduce manual processes." | "a) System supports integration with other HR systems. b) Data flows seamlessly between systems. c) Integration reduces the need for manual data entry and errors." | "Reduces manual processes by integrating with other HR systems." |  |  | 9 | 18
| Total do tema 'Legal and Executive Reviews' |  |  | 0.0 pontos
User Stories for Accessibility and Interface | 8.1 | "As an HR manager, I want an intuitive interface so that I can easily navigate and use the system without extensive training." | "a) Interface is user-friendly and easy to navigate. b) Common tasks can be performed with minimal clicks. c) User feedback is positive regarding ease of use." | "Ensures ease of use for HR managers." |  |  | 5 | 10
| 8.2 | "As a mobile user, I want to access the system on my mobile device so that I can perform HR tasks on the go." | "a) System is accessible via mobile devices. b) Mobile interface is responsive and functional. c) All key features are available on mobile devices." | "Supports mobile access for users on the go." |  |  | 6 | 12
| 8.3 | "As an HR employee, I want the system to be accessible to users with disabilities so that everyone in the organization can use it effectively." | "a) System meets accessibility standards (e.g., WCAG 2.1). b) Features such as screen readers, keyboard navigation, and high contrast modes are supported. c) Accessibility is tested and verified by users with disabilities." | "Ensures accessibility for all users." |  |  | 7 | 14
| 8.4 | "As a new user, I want a guided tour when I first log in so that I can quickly understand how to use the system." | "a) System provides an optional guided tour for new users. b) Guided tour covers key features and navigation. c) Users can skip or revisit the tour as needed." | "Helps new users quickly understand the system." |  |  | 4 | 8
| 8.5 | "As an HR manager, I want customizable dashboards so that I can see the information that is most relevant to me." | "a) Users can customize their dashboards with relevant widgets. b) Customizations are saved and persist across sessions. c) Users can reset dashboards to default settings if needed." | "Allows HR managers to view relevant information easily." |  |  | 6 | 12
| 8.6 | "As a system administrator, I want role-based access controls so that users only see and interact with features relevant to their roles." | "a) System supports role-based access controls. b) Different user roles have appropriate permissions. c) Access controls are easy to configure and manage." | "Ensures users see only relevant features based on their roles." |  |  | 5 | 10
| 8.7 | "As an HR employee, I want quick access to help and support resources so that I can resolve any issues I encounter." | "a) Help and support resources are easily accessible within the system. b) Resources include FAQs, tutorials, and contact information for support. c) Users can provide feedback on the usefulness of support resources." | "Provides easy access to support for resolving issues." |  |  | 4 | 8
| 8.8 | "As an HR manager, I want to receive notifications for important events and updates so that I stay informed about critical tasks and changes." | "a) Users can configure notification preferences. b) Notifications are sent for important events and updates. c) Users can view notification history and details." | "Keeps HR managers informed about critical tasks and changes." |  |  | 5 | 10
| 8.9 | "As a multilingual user, I want the system to support multiple languages so that I can use it in my preferred language." | "a) System supports multiple languages. b) Users can select their preferred language. c) Translations are accurate and cover all interface elements." | "Ensures the system can be used by users in their preferred language." |  |  | 6 | 12
| 8.1 | "As an HR manager, I want to generate custom reports so that I can analyze data according to specific criteria." | "a) Users can create and customize reports. b) Reports can be saved, exported, and shared. c) Custom reports meet user-defined criteria and display accurate data." | "Allows HR managers to analyze data based on specific criteria." |  |  | 7 | 14
| Total do tema 'Accessibility and Interface' |  |  | 0.0 pontos
User Stories for Security and Data Privacy | 9.1 | "As a system administrator, I want role-based access controls so that users only have access to data and features relevant to their roles." | "a) System supports role-based access controls. b) Access controls are easy to configure and manage. c) Users only access data and features relevant to their roles." | "Ensures users have appropriate access based on roles." |  |  | 6 | 12
| 9.2 | "As an HR manager, I want sensitive data to be encrypted so that employee information is protected." | "a) System encrypts sensitive data at rest and in transit. b) Encryption standards meet industry best practices. c) Encrypted data can be decrypted only by authorized users." | "Protects sensitive employee data through encryption." |  |  | 5 | 10
| 9.3 | "As an HR employee, I want the system to log all access and changes to data so that there is a record of who did what and when." | "a) System logs all access and data changes. b) Logs include details such as user ID, timestamp, and action performed. c) Logs can be reviewed by authorized personnel for audit purposes." | "Maintains an audit trail for data access and changes." |  |  | 5 | 10
| 9.4 | "As a system administrator, I want to perform regular security audits so that the system remains secure and compliant with policies." | "a) System supports regular security audits. b) Audit results are documented and reviewed. c) Identified issues are addressed promptly." | "Ensures regular security checks and compliance. |  |  | 7 | 14
| 9.5 | "As an HR manager, I want to ensure that user passwords are strong and periodically updated so that unauthorized access is prevented." | "a) System enforces strong password policies. b) Users are prompted to update passwords periodically. c) Passwords meet complexity requirements (e.g., length, characters)." | "Prevents unauthorized access through strong password policies." |  |  | 4 | 8
| 9.6 | "As a system administrator, I want to use two-factor authentication (2FA) so that access to the system is more secure." | "a) System supports two-factor authentication. b) 2FA is required for all administrative accounts. c) 2FA methods (e.g., SMS, authenticator apps) are reliable and secure." | "Enhances security through two-factor authentication." |  |  | 6 | 12
| 9.7 | "As an HR employee, I want to be notified of any unauthorized access attempts so that I can take appropriate action." | "a) System sends notifications for unauthorized access attempts. b) Notifications include details of the attempt (e.g., IP address, timestamp). c) Users can review and respond to access attempt notifications." | "Alerts users to unauthorized access attempts." |  |  | 5 | 10
| 9.8 | "As an HR manager, I want to ensure that data backups are performed regularly so that data can be recovered in case of loss or corruption." | "a) System performs regular data backups. b) Backups are stored securely and can be restored quickly. c) Backup procedures are documented and tested periodically." | "Ensures data recovery through regular backups." |  |  | 5 | 10
| 9.9 | "As a system administrator, I want to control access to the system based on IP addresses so that only trusted networks can access sensitive data." | "a) System supports IP-based access controls. b) Access is restricted to trusted IP addresses. c) IP restrictions can be configured and updated as needed." | "Restricts access based on IP addresses." |  |  | 6 | 12
| 9.1 | "As an HR manager, I want to anonymize data in reports so that sensitive information is protected while analyzing trends and metrics." | "a) System supports data anonymization in reports. b) Anonymized reports do not include personally identifiable information. c) Anonymization methods ensure data privacy while maintaining report utility." | "Protects sensitive information through data anonymization." |  |  | 7 | 14
| Total do tema 'Security and Data Privacy' |  |  | 0.0 pontos
User Stories for Scalability | 10.1 | "As a system architect, I want the system to handle an increasing number of users so that it supports organizational growth." | "a) System supports scaling up to thousands of concurrent users. b) Performance remains stable under high user load. c) Load testing demonstrates system stability and responsiveness." | "Ensures the system can grow with the organization and handle increased user load." |  |  | 8 | 16
| 10.2 | "As a database administrator, I want the database to efficiently manage large volumes of data so that performance is not compromised." | "a) Database supports horizontal and vertical scaling. b) Data retrieval times remain consistent as data volume grows. c) Regular database performance optimization is performed." | "Maintains database performance as data volume increases." |  |  | 7 | 14
| 10.3 | "As an IT manager, I want to implement load balancing so that system performance is optimized under varying loads." | "a) Load balancers distribute traffic evenly across servers. b) System remains responsive under peak loads. c) Load balancing configuration can be adjusted dynamically." | "Optimizes system performance through effective load distribution." |  |  | 6 | 12
| 10.4 | "As a system administrator, I want to use cloud infrastructure so that the system can scale resources as needed." | "a) System is deployed on a scalable cloud platform. b) Resources (CPU, memory, storage) can be scaled up/down automatically. c) Cloud provider's scaling features are utilized effectively." | "Utilizes cloud scalability features to handle resource needs dynamically." |  |  | 8 | 16
| 10.5 | "As a system architect, I want to implement microservices architecture so that individual components can be scaled independently." | "a) System is designed using microservices architecture. b) Each microservice can be scaled independently. c) Communication between microservices is efficient and reliable." | "Allows independent scaling of system components for better resource management." |  |  | 7 | 14
| 10.6 | "As a DevOps engineer, I want to use containerization so that the system can be easily deployed and scaled across different environments." | "a) System components are containerized (e.g., using Docker). b) Containers can be orchestrated and scaled using tools like Kubernetes. c) Deployment processes are automated and reliable." | "Facilitates easy deployment and scaling through containerization and orchestration tools." |  |  | 6 | 12
| 10.7 | "As an IT manager, I want to ensure that system updates and maintenance do not impact scalability so that the system remains performant." | "a) System updates are applied without downtime. b) Maintenance tasks do not degrade performance. c) Rolling updates and blue-green deployments are used." | "Maintains system performance during updates and maintenance tasks." |  |  | 5 | 10
| 10.8 | "As a performance engineer, I want to conduct regular performance testing so that any scalability issues are identified and addressed early." | "a) Regular performance and stress tests are conducted. b) Test results are analyzed to identify potential bottlenecks. c) Performance tuning is performed based on test results." | "Identifies and resolves scalability issues early through regular testing." |  |  | 6 | 12
| 10.9 | "As a system architect, I want to ensure the system supports multi-tenancy so that it can serve multiple organizations efficiently." | "a) System supports multi-tenancy with data isolation. b) Tenants can be added without significant changes to the system. c) Performance remains stable as the number of tenants increases." | "Supports multiple organizations efficiently with isolated data for each tenant." |  |  | 7 | 14
| 10.10 | "As a security engineer, I want to ensure that scaling does not compromise security so that data remains protected." | "a) Security measures are maintained as the system scales. b) Access controls and encryption are consistently applied. c) Regular security audits are conducted during scaling processes." | "Ensures data security and access control measures are maintained during scaling." |  |  | 5 | 10
Total do tema 'Scalability'
User Stories for Reliability and Availability | 11.1 | "As a system administrator, I want the system to have high availability so that users can access it at any time." | "a) System uptime is maintained at 99.9% or higher. b) Failover mechanisms are in place and tested regularly. c) System monitoring alerts administrators to downtime or issues." | "Ensures system accessibility and reliability for users at all times." |  |  | 8 | 16
| 11.2 | "As a database administrator, I want to implement database redundancy so that data is not lost during failures." | "a) Database replicas are maintained in multiple locations. b) Automated failover to backup databases is configured. c) Regular backups are performed and tested for data integrity." | "Prevents data loss and ensures data availability during failures." |  |  | 7 | 14
| 11.3 | "As a DevOps engineer, I want to use continuous monitoring so that system health is constantly checked and issues are detected early." | "a) Continuous monitoring tools are implemented (e.g., Nagios, Prometheus). b) Alerts are configured for critical system metrics. c) Monitoring dashboards are available for real-time system status." | "Allows early detection and resolution of system issues." |  |  | 6 | 12
| 11.4 | "As an IT manager, I want to conduct regular disaster recovery drills so that the team is prepared for real incidents." | "a) Disaster recovery drills are conducted quarterly. b) Recovery time objectives (RTO) and recovery point objectives (RPO) are met. c) Lessons learned from drills are documented and used to improve plans." | "Prepares the team for effective response to real incidents." |  |  | 7 | 14
| 11.5 | "As a system architect, I want to design the system with fault tolerance so that it can handle component failures gracefully." | "a) System components have built-in redundancy. b) Failure of one component does not affect overall system availability. c) Automatic recovery from component failures is tested and verified." | "Ensures system resilience against component failures." |  |  | 8 | 16
| 11.6 | "As a performance engineer, I want to implement load balancing so that the system can distribute traffic evenly and avoid overloading any single component." | "a) Load balancing solutions (e.g., HAProxy, Nginx) are implemented. b) Traffic is evenly distributed across multiple servers. c) Load balancers are configured to handle sudden spikes in traffic." | "Optimizes system performance through effective traffic distribution." |  |  | 6 | 12
| 11.7 | "As a system administrator, I want to ensure regular maintenance does not affect system availability so that users experience minimal disruption." | "a) Maintenance windows are scheduled during off-peak hours. b) Rolling updates and blue-green deployments are used. c) Users are notified in advance of any planned maintenance." | "Maintains system availability during regular maintenance tasks." |  |  | 5 | 10
| 11.8 | "As a security engineer, I want to ensure system reliability and availability are not compromised by security measures so that the system remains secure and performant." | "a) Security measures are integrated without significant performance impact. b) Regular security audits and penetration tests are conducted. c) Security incidents are logged and responded to promptly." | "Balances security measures with system performance and availability." |  |  | 6 | 12
| 11.9 | "As a system architect, I want to implement auto-scaling so that the system can automatically adjust resources based on load." | "a) Auto-scaling policies are defined and implemented. b) System resources are scaled up/down based on real-time demand. c) Auto-scaling events are logged and reviewed for optimization." | "Ensures the system can dynamically adjust resources to meet demand." |  |  | 7 | 14
| 11.10 | "As an IT manager, I want to ensure there is a clear incident response plan so that the team can respond quickly and effectively to any system issues." | "a) An incident response plan is documented and accessible. b) Team members are trained on the incident response procedures. c) Post-incident reviews are conducted to improve response strategies." | "Provides a clear plan for quick and effective incident response." |  |  | 5 | 10
Total do tema 'Reliability and Availability'
Support and Maintenance | 12.1 | "As a system administrator, I want to have regular system updates so that the system remains secure and functional." | "a) Updates are scheduled and performed regularly. b) Patch notes are documented and communicated to relevant stakeholders. c) System performance is tested post-update to ensure stability." | "Ensures system security and functionality through regular updates." |  |  | 6 | 12
| 12.2 | "As an IT manager, I want to provide technical support to users so that they can resolve issues quickly." | "a) A helpdesk is available during business hours. b) Support tickets are tracked and managed through a ticketing system. c) User issues are resolved within the agreed service level agreements (SLAs)." | "Provides timely and effective technical support to users." |  |  | 7 | 14
| 12.3 | "As a system administrator, I want to perform regular system maintenance so that the system operates efficiently." | "a) Maintenance schedules are planned and communicated in advance. b) System health checks are performed during maintenance. c) System logs are reviewed and analyzed for any anomalies." | "Ensures efficient system operation through regular maintenance." |  |  | 5 | 10
| 12.4 | "As a support engineer, I want to have access to a knowledge base so that I can provide accurate and consistent support." | "a) A comprehensive knowledge base is maintained and updated regularly. b) Support engineers have access to the knowledge base. c) Knowledge base articles are reviewed and validated for accuracy." | "Enables support engineers to provide accurate and consistent support." |  |  | 6 | 12
| 12.5 | "As a DevOps engineer, I want to implement automated monitoring so that system issues can be detected and addressed promptly." | "a) Monitoring tools are set up to track system performance and health. b) Alerts are configured for critical metrics. c) Automated responses are set up for common issues." | "Detects and addresses system issues promptly through automated monitoring." |  |  | 7 | 14
| 12.6 | "As a user, I want to have access to self-service support options so that I can resolve minor issues on my own." | "a) A self-service portal is available with FAQs and troubleshooting guides. b) Users can access the portal 24/7. c) Common issues and their resolutions are documented and accessible." | "Empowers users to resolve minor issues independently." |  |  | 5 | 10
| 12.7 | "As a system administrator, I want to conduct regular backups so that data is protected and can be restored if necessary." | "a) Backup schedules are defined and adhered to. b) Backup data is stored securely. c) Restoration procedures are tested regularly." | "Protects data and ensures its availability through regular backups." |  |  | 6 | 12
| 12.8 | "As an IT manager, I want to ensure the system is scalable so that it can handle growth and increased demand." | "a) Scalability requirements are defined and documented. b) System capacity is monitored and adjusted as needed. c) Scalability tests are performed to ensure the system can handle increased load." | "Ensures the system can handle growth and increased demand." |  |  | 7 | 14
| 12.9 | "As a user, I want to be informed about any scheduled maintenance so that I can plan my work accordingly." | "a) Maintenance notifications are sent out in advance. b) Users are informed of the expected duration and impact. c) Follow-up notifications are sent once maintenance is completed." | "Keeps users informed about scheduled maintenance and its impact." |  |  | 5 | 10
| 12.10 | "As a system administrator, I want to have a disaster recovery plan so that the system can recover quickly from major incidents." | "a) A disaster recovery plan is documented and tested. b) Recovery time objectives (RTO) and recovery point objectives (RPO) are defined. c) Regular disaster recovery drills are conducted." | "Ensures quick recovery from major incidents through a well-defined disaster recovery plan." |  |  | 8 | 16
Total do tema ' Support and Maintenance'
Total do Backlog 'Gestão de Recursos Humanos '